PRODUCT REQUIREMENTS DOCUMENT

AI-Powered BIN Procurement Tracker

Intelligent project management for New Bank Identification Number (BIN) procurement workflows — from network request through card launch.

| Version | 1.0 |
| --- | --- |
| Date | May 2026 |
| Author | Robin Khatwani |
| Status | Draft |
| Domain | Card Payments / FinTech |
| Stakeholders | Issuer · Network · Processor · Embosser |

# Table of Contents

# 1. Problem Definition

## Background

Launching a new payment card requires procuring a Bank Identification Number (BIN) from the card network (e.g., Mastercard, Visa). This is a complex, multi-party process involving the Issuer (the bank or card company), the Network (scheme provider), the Processor (transaction processor), and the Embosser (card manufacturer). Collectively, these parties must coordinate across 31 sequential and parallel steps spanning approximately 5 months.

## Core Pain Points

| # | Pain Point | Impact | Affected Party |
| --- | --- | --- | --- |
| P1 | Manual status tracking in spreadsheets — All 31 steps tracked in a static Excel file with no automation or alerting | High — steps missed or delayed undetected | All parties |
| P2 | No cross-party visibility — Issuer, Network, Processor, and Embosser cannot see each other's status in real time | High — delays cascade across dependencies | Issuer, Network, Processor |
| P3 | No dependency management — Steps like Card Keys Exchange depend on Card Keys Generation, but the tracker has no logic to enforce or alert on this | High — out-of-sequence actions cause compliance issues | Network, Processor |
| P4 | No intelligent reminders or escalations — Project managers rely on manual follow-up with each party | Medium — PM bandwidth wasted on chasing status | PM, Issuer |
| P5 | No risk prediction — Delays in early steps are not flagged as risks to downstream milestones | High — launch date jeopardized without early warning | Issuer, Network |
| P6 | Key management steps lack security guardrails — Steps 9-12 (Card Key Authorization, Generation, Exchange) are tracked the same as administrative steps | Critical — regulatory and fraud risk | Processor, Network |

## Problem Statement

BIN procurement for new card launches is a high-stakes, multi-party, sequentially dependent process currently managed through static spreadsheets with no automation, no real-time visibility, no dependency intelligence, and no risk prediction — resulting in delays, compliance gaps, and excessive PM overhead.

## Current State vs. Desired State

| Dimension | Current State | Desired State |
| --- | --- | --- |
| Status Tracking | Manual Excel / Smartsheet, updated ad hoc | Real-time, auto-updated dashboard |
| Stakeholder Visibility | Email chains per step | Shared portal with role-based views |
| Risk Detection | Reactive (after delays occur) | Proactive AI-driven risk scoring |
| Reminders | Manual PM follow-up | Automated, context-aware nudges |
| Security Steps | Treated same as admin steps | Elevated controls, HSM audit trail |
| Audit Trail | None | Full immutable log per step |

# 2. Solution Definition

## Product Vision

An AI-powered BIN Procurement Tracker — a collaborative, intelligent project management platform purpose-built for payment card launch workflows. The system ingests project milestones from Excel, Smartsheet, or Jira; tracks multi-party progress; predicts risks using AI; and automates stakeholder communication — reducing card launch time and eliminating manual coordination overhead.

## Core Capabilities

| Capability | Description | AI-Powered? |
| --- | --- | --- |
| Milestone Tracker | Centralized dashboard showing all 31 steps, responsible parties, estimated vs. actual dates, and current status | No (Core) |
| Multi-source Import | Project data ingested from Excel (.xlsx), Smartsheet (via API or CSV export), or Jira (via REST API) | No (Core) |
| Dependency Engine | Automatically blocks downstream steps when upstream steps are incomplete; sends blocking alerts | No (Rule-based) |
| AI Risk Predictor | Analyses current step delays and estimates probability of missing launch date; flags critical path deviations | Yes |
| Smart Nudges | AI-generated, context-aware reminder messages sent to responsible parties based on step urgency and history | Yes |
| Status Summariser | Weekly AI-generated narrative summary of project health for executive stakeholders | Yes |
| Secure Key Workflow | Steps 9-12 (Card Key workflows) handled with elevated access controls and HSM integration markers | No (Compliance) |
| Multi-party Portal | Role-based access for Issuer, Network, Processor, Embosser — each sees their own tasks plus dependencies | No (Core) |
| Audit Log | Immutable timestamped record of every status change, comment, and escalation per step | No (Compliance) |

## Solution Architecture

Data Layer: Project configuration imported from Excel, Smartsheet (API/CSV), or Jira (REST API), or entered via UI. Data stored in a relational DB with event sourcing for audit logs.

Intelligence Layer: An LLM-based AI engine (Claude / GPT-4o class) handles risk prediction, reminder generation, and status summarisation. Prompts are structured, deterministic, and auditable.

Presentation Layer: A web portal with role-based dashboards, a timeline view, and an API for integration with existing PM tools (Jira, Smartsheet, ServiceNow, etc.).

## Key User Stories

| Role | As a... | I want to... | So that... |
| --- | --- | --- | --- |
| Program Manager | PM at the Issuer | See all 31 steps on one screen with RAG status | I can intervene before delays cascade |
| Network PM | Network PM | Receive smart reminders only for my steps | I am not overwhelmed by irrelevant notifications |
| Processor | Processor security team | Complete key steps with elevated approval workflow | Compliance and audit requirements are met |
| Executive | Card launch sponsor | Receive a weekly AI summary of project health | I can report to the board without manual data gathering |

# 3. Core Metrics

North Star Metric: On-Time Card Launch Rate — % of BIN procurement projects completed on or before target launch date. Target: >= 90% within 6 months of deployment.

## Product Metrics

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Step On-Time Rate | >= 85% | % of 31 steps completed by estimated date |
| Average Step Delay | < 3 days | Average slippage per step vs. plan |
| PM Time Saved | 40% | Reduction in manual follow-up hours per launch |
| AI Nudge Response Rate | >= 70% | % of AI reminders resulting in status update within 24h |
| Risk Detection Precision | >= 80% | % of AI-flagged risks that actually caused delay |
| Audit Coverage | 100% | % of steps with immutable audit trail |

## Business Metrics

| Metric | Baseline | 6-Month Target |
| --- | --- | --- |
| Average BIN procurement cycle time | ~5 months (manual) | < 4 months |
| Failed or delayed launches due to BIN issues | ~30% of projects | < 10% |
| Customer (Issuer) NPS | Not measured | >= 40 |

# 4. Prioritization

Features are prioritised using the MoSCoW framework. Phase 1 covers Must Have features; Phases 2-3 address Should Have and Could Have.

## Must Have — Phase 1 (MVP)

- All 31-step milestone tracker with status (To Do / In Progress / Done / Blocked)

- Excel (.xlsx) and Smartsheet CSV / API import for project configuration

- Jira REST API import as an equivalent configuration source

- Estimated vs. actual date tracking per step

- Responsible party assignment per step

- Basic dependency blocking (step N+1 cannot start until step N complete)

- Email reminders for overdue steps

- Full immutable audit log per step

- Role-based access: Issuer, Network, Processor, Embosser

- Elevated workflow for Card Key steps (9-12)

## Should Have — Phase 2

- AI-powered risk predictor (launch date delay probability)

- AI smart nudges — context-aware, personalised reminder text

- Executive weekly AI status summary

- Critical path highlighting on timeline view

- Multi-project dashboard (multiple BIN procurements in parallel)

- Slack / Teams integration for in-app notifications

- Jira / Smartsheet / ServiceNow bi-directional task sync

## Could Have — Phase 3

- AI chatbot — natural language project status queries

- Predictive benchmarking vs. industry average launch times

- HSM key ceremony digital workflow integration

- Mobile app for on-the-go status updates

- Document vault per step (SOW, approval letters, non-liability letters)

## Won't Have (This Release)

- Full ERP integration (SAP, Oracle)

- Physical HSM management

- Card design tooling

- Customer-facing cardholder features

- Network billing / settlement processing

# 5. Roadmap

| Phase | Timeline | Theme | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1 | Jun – Jul 2026 | Core Tracker + Portal | 31-step tracker, Excel/Smartsheet/Jira import, role-based portal, dependency blocking, email reminders, audit log, Card Key elevated workflow |
| Phase 2 | Aug – Sep 2026 | AI Intelligence Layer | AI risk predictor, AI smart nudges, weekly AI executive summary, critical path highlighting, Slack/Teams integration, Jira & Smartsheet bi-directional sync |
| Phase 3 | Oct – Dec 2026 | Extended Intelligence | Conversational AI chatbot, benchmarking vs. industry timelines, document vault, MDES tokenisation readiness check, HSM digital ceremony, mobile app |
| Phase 4 | Q1 2027 | Enterprise Scale | ERP integrations (SAP/Oracle), multi-region BIN support, ServiceNow connector, SOC 2 Type II, white-label offering |

# 6. Evaluation Plan

## Testing Strategy

| Test Type | Scope | Responsible | Exit Criteria |
| --- | --- | --- | --- |
| Unit Testing | Dependency engine, date calculation, step state machine | Engineering | 100% coverage on dependency and state logic |
| Integration Testing | Excel/Smartsheet/Jira import, Jira sync, email/Slack triggers | Engineering + QA | Zero data loss on import; notification delivery >= 99% |
| UAT — Phase 1 | 2 pilot Issuer PMs complete a simulated BIN procurement in the tracker | Product + Pilot Users | Task success rate >= 90%; SUS score >= 70 |
| AI Prompt Evaluation | Risk predictor and nudge generator tested on 20 historical project datasets | AI/ML team + Product | Risk detection precision >= 80%; nudge relevance >= 4/5 |
| Security Testing | Role-based access, card key elevated workflow, audit log integrity | Security team | Zero privilege escalation; audit log tamper-proof |
| Performance Testing | Dashboard load with 50 concurrent projects, 200 concurrent users | Engineering | Page load < 2s at P95; API response < 500ms at P95 |

## AI Evaluation Framework

| AI Feature | Evaluation Method | Target Score |
| --- | --- | --- |
| Risk Predictor | Compare AI delay flags vs. actual delays in 20 historical projects (precision/recall) | Precision >= 0.80, Recall >= 0.75 |
| Smart Nudges | Human rater panel (5 PMs) score relevance, tone, urgency on 50 generated nudges | Avg. rating >= 4.0 / 5.0 |
| Weekly Summary | Executive users rate weekly summaries for accuracy and clarity | Avg. rating >= 4.2 / 5.0 |
| Chatbot (Ph. 3) | 100-question benchmark; compare answer accuracy vs. ground truth project data | Accuracy >= 90% |

# 7. Prompt Strategy

## Design Principles

All prompts follow four principles: Grounded (always use real project data, never hallucinate), Scoped (output length and format are explicitly constrained), Role-aware (audience and tone vary by recipient), and Auditable (every AI output is logged with its input context for traceability).

## Prompt Templates

| Prompt | Trigger | Output Format | Length Limit |
| --- | --- | --- | --- |
| Risk Predictor | Nightly, or when any step is marked overdue | JSON: {risk_score, risk_factors[], mitigation} | Structured JSON |
| Smart Nudge | Step is overdue or approaching deadline | Plain prose reminder message | < 80 words |
| Weekly Summary | Every Monday morning; sent to Issuer executive sponsor | Business prose narrative, RAG status | < 200 words |
| Project Chatbot | User natural language question (Phase 3) | Plain prose answer, grounded in project data only | < 3 sentences |

## AI Guardrails

- Input validation on all data injected into prompts

- Output length limits enforced on every prompt

- No PII in prompts — step owners are anonymised before injection

- All AI outputs reviewed by PM before escalation actions are taken

- Confidence score threshold: risk score only sent if model confidence > 0.75

- Human override on every AI suggestion — no fully autonomous actions

- All AI prompt/response pairs stored in immutable audit log

# 8. Responsible AI Risk & Mitigation

This product operates in the regulated payments domain. AI features interact with sensitive project data including card key management workflows, non-liability letters, and multi-party settlement processes. All AI risks below are assessed with this context in mind.

| Risk | Category | Severity | Mitigation |
| --- | --- | --- | --- |
| AI hallucination in risk prediction — fabricated delay scenario causes false escalation | Accuracy | HIGH | Strict grounded prompting; confidence threshold >= 0.75; human PM review before any escalation action |
| Sensitive key management data in prompts — Steps 9-12 include cryptographic references | Security | HIGH | Key steps are AI-excluded by default; AI receives only step status (ToDo/Done), never key values or HSM references |
| Biased nudge tone causing stakeholder friction | Fairness / Tone | MEDIUM | Explicit tone guardrail in system prompt; PM can edit before send; A/B test nudge variants |
| Over-reliance on AI risk score — PM stops exercising independent judgment | Human Oversight | MEDIUM | AI outputs clearly labelled 'AI Suggested'; training material for PMs on AI limitations; mandatory override option |
| Data residency / cross-border PII — project data shared across jurisdictions | Privacy / Compliance | HIGH | PII stripped before LLM prompt injection; regional data residency options; GDPR Article 25 compliance |
| AI chatbot gives incorrect compliance guidance on non-liability letter requirements | Accuracy / Legal | HIGH | Chatbot strictly grounded in project data; legal questions redirected to human experts; clear disclaimer |
| LLM provider dependency / availability risk | Operational | MEDIUM | Graceful degradation to rule-based reminders if LLM unavailable; multi-provider strategy |

## AI Governance Commitments

- Human-in-the-loop for all consequential AI actions

- No AI training on customer project data without explicit consent

- Full audit trail of every AI prompt and output

- Quarterly AI risk review with security team

- AI feature toggle — any AI capability can be disabled per customer

# 9. Pricing & Cost Structure

## Pricing Model

The platform uses a per-project SaaS subscription model, billed annually. Pricing scales with the number of active BIN procurement projects and the AI feature tier.

| Plan | Price | Concurrent Projects | Key Features |
| --- | --- | --- | --- |
| Starter | $2,500 / project / year | Up to 3 | 31-step tracker, Excel/Smartsheet import, role-based portal, rule-based reminders, audit log |
| Professional | $6,500 / project / year | Up to 10 | Everything in Starter + AI risk predictor, AI smart nudges, AI executive summary, Slack/Teams, Jira & Smartsheet sync |
| Enterprise | Custom annual contract | Unlimited | Everything in Professional + AI chatbot, HSM ceremony workflow, white-label, dedicated CSM, SOC 2 Type II, SLA |

## Annual Cost Structure (100 Active Projects)

| Category | Item | Annual Cost | % of Revenue |
| --- | --- | --- | --- |
| Infrastructure | Cloud hosting (compute + storage + DB) | $48,000 | 8% |
| Infrastructure | CDN + email delivery | $6,000 | 1% |
| Infrastructure | Security tooling (WAF, SIEM, secrets mgmt) | $24,000 | 4% |
| AI / LLM | LLM API calls (~3M tokens/month) | $36,000 | 6% |
| AI / LLM | AI evaluation infrastructure | $12,000 | 2% |
| Compliance | SOC 2 audit + pen testing | $40,000 | 7% |
| Compliance | PCI DSS advisory | $20,000 | 3% |
| Engineering | Dev + QA (3 FTE blended) | $360,000 | 60% |
| Product & GTM | Product + Sales + Customer Success | $54,000 | 9% |
| TOTAL |  | $600,000 | 100% |

# 10. Pilot Technical Scope — Live Status Tracker

The pilot technical scope covers four concrete deliverables that bring the BIN Procurement Tracker to life as a working local web application — reading live data from Excel, Smartsheet CSV, or Jira export and serving it through a browser-accessible dashboard.

## a. Status Tracker HTML with Executive Summary

A dynamically generated HTML page served at /bin-tracker that provides:

| Component | Content | Data Source |
| --- | --- | --- |
| RAG Status Badge | Green / Amber / Red — computed from overdue step count | Step statuses + estimated dates |
| Progress Bar | Visual % completion (Done steps / Total steps) | Step status column |
| Days to Launch | Live countdown to target launch date (10 Oct 2026) | System clock |
| Summary KPI Tiles | Total / Done / In Progress / To Do / Overdue / % Complete | All rows |
| Stakeholder Donuts | 4 SVG donut charts — Issuer, Network, Processor, Embosser — by status | Responsible column + status |
| Overdue Alert Panel | Red highlighted list of every step past estimated date | Estimated date vs. today |
| Next Milestones Cards | 3 upcoming pending steps with owner badge and due date | First pending steps |
| All-Steps Table | 31 rows: Step, Description, Responsible, Dates, Status, Days Countdown | All Excel/Smartsheet rows |

## b. Local Server Hosting (server.py)

A Python HTTP server built entirely on the standard library (no pip installs required). Reads the Excel/Smartsheet/Jira source file fresh on every request.

| Property | Value |
| --- | --- |
| Language | Python 3 — standard library only (http.server, zipfile, xml.etree) |
| Port | 8080 (configurable via PORT constant) |
| Host | localhost (127.0.0.1) — accessible only from the local machine |
| Data read | On every incoming HTTP request — zero caching |
| Input sources | Excel (.xlsx), Smartsheet CSV export, or Jira CSV export |
| Auto-start | Configured via macOS launchd (runs automatically at every login) |
| To start | bash ~/Desktop/Robin AI Learnings/setup_autostart.sh |

## c. Landing Page

A professional project hub landing page at http://localhost:8080 with the heading 'Robin Khatwani Projects'. Contains a hyperlinked card to the BIN Procurement Status Tracker and explains the live data behaviour.

## d. Live Data Refresh Mechanism

| Layer | Mechanism | Effect |
| --- | --- | --- |
| Server-side read-on-request | Python server opens and parses the source file on every HTTP GET | Every click reads the latest saved data |
| HTTP no-cache headers | Cache-Control: no-cache, no-store, must-revalidate sent on every response | Browser never serves a cached version |
| 60-second auto-refresh | JavaScript countdown timer calls location.reload() — also shows live countdown in header | Page auto-refreshes even if left open |

## How to Run

- Open Terminal on your Mac

- Run: bash ~/Desktop/Robin\ AI\ Learnings/setup_autostart.sh

- Open browser to http://localhost:8080

- Click 'View Live Tracker' to open the BIN Procurement Status Tracker

- Update any step in Excel or Smartsheet, save, then click 'Refresh Now'

- Press Ctrl+C in Terminal to stop the server (auto-start will restart it at next login)