## Card BIN Project
Project Objective : - To Track progress of New BIN procurement for New Card launch.
Steps | Description | Responsible | Notes | Current Status | Estimated Date | Completion Date
1 | Request for Project to Network | Issuer | s | Done | 2026-05-01 | 2026-05-01
2 | Project Creation and PM Assignment | Network |  | In Progress | 2026-06-05
3 | Project SOW Preparation | Issuer |  | ToDo | 2026-06-15
4 | Project SOW Approval | Issuer |  | ToDo | 2026-06-18
5 | Project Plan Proposal | Network |  | ToDo | 2026-06-25
6 | Project Plan Approval | Issuer |  | ToDo | 2026-07-01
7 | New Account BIN Ordering | Issuer |  | ToDo | 2026-07-05
8 | New Account BIN Available | Network |  | ToDo | 2026-07-10
9 | Processor Authorization for Card Keys | Issuer |  | ToDo | 2026-07-15
10 | Card Keys Generation | Processor |  | ToDo | 2026-07-20
11 | Card Keys Exchange | Network and Processor |  | ToDo | 2026-07-31
12 | Key Updates in Processor System | Processor |  | ToDo | 2026-08-05
13 | Key Updates in Network System | Network |  | ToDo | 2026-08-08
14 | Non Liability Letter to Network | Issuer |  | ToDo | 2026-08-12
15 | Network Settlement End Point Initiation | Network |  | ToDo | 2026-08-12
16 | Network Settlement End Point Approval | Issuer |  | ToDo | 2026-08-20
17 | File Encryption Key Exchange | Network and Processor |  | ToDo | 2026-08-25
18 | Account BIN Setup in Blocked State | Network |  | ToDo | 2026-08-28
19 | Account BIN and Settlement End Point Go Live | Network |  | ToDo | 2026-08-31
20 | MDES Project Enablement | Network |  | ToDo | 2026-09-02
21 | Token BIN Assignment | Network |  | ToDo | 2026-09-04
22 | Token BIN Live | Network |  | ToDo | 2026-09-08
23 | Account BIN Block Removal Initiation | Issuer |  | ToDo | 2026-09-09
24 | Account BIN Block Removal Completion | Network |  | ToDo | 2026-09-13
25 | Account Setup and Card Ordering | Issuer and Processor |  | ToDo | 2026-09-20
26 | Card Fulfillment and Personalization | Embosser and Processor |  | ToDo | 2026-09-25
27 | Card Shipping | Embosser |  | ToDo | 2026-09-28
28 | Card Receiving and Activation | Issuer and Processor |  | ToDo | 2026-09-30
29 | Card Transaction Validation | Issuer and Processor |  | ToDo | 2026-10-02
30 | Settlement Verification | Issuer and Processor |  | ToDo | 2026-10-07
31 | Project Close | Issuer |  | ToDo | 2026-10-10